## Trials
# | Trial | Trial status | HRA approval | Site selected | Pharmacy notified | Pharmacy set-up start | Aseptic | Aseptic BMR authorised | Prescribing system | iQemo Template set up | iQemo template authorised | Pharmacy green light | Trial Complexity | ePMA Complexity | Priority score | Trial phase | Notes
1 | RINVIL-301 |  | 2026-06-10 | 2026-08-21 | 2026-08-25 | 2026-08-29 | Y |  | chemo ePMA | 2026-09-13 |  |  | Complex | Moderate | 35 | 3
2 | SORNOV-3 |  | 2026-07-05 | 2026-08-28 | 2026-08-31 | 2026-09-03 | Y |  | chemo ePMA | 2026-09-18 |  |  | Moderate | Complex | 30 | 3
3 | TORDAX |  | 2026-07-20 | 2026-09-02 | 2026-09-05 | 2026-09-08 | N |  | none |  |  |  | Simple |  |  | 2
4 | ELQUINTA-03 |  | 2026-07-30 | 2026-09-08 | 2026-09-11 |  | Y |  | inpatient ePMA |  |  |  | Moderate | Simple | 25 | 2 | Sponsor documents still awaited.
5 | MIRNO |  | 2026-08-05 | 2026-09-09 | 2026-09-14 | 2026-09-18 | N |  | chemo ePMA | 2026-10-03 |  |  | Moderate | Moderate |  | 3
6 | ARSTE |  | 2026-08-09 | 2026-09-12 | 2026-09-16 |  | N |  | none |  |  |  | Simple |  | 28.5 | 2
7 | SELHE |  | 2026-08-11 | 2026-09-16 | 2026-09-19 | 2026-09-23 | Y |  | none |  |  |  | Complex |  | 35 | 3
8 | CORPEX (DGT-9102) |  | 2026-08-14 | 2026-09-18 | 2026-09-22 |  | Y |  | chemo ePMA | [6 empty] | 1 to 2 | Complexity not yet assessed.
9 | DROMON (GLT-3008) |  | 2026-08-19 | 2026-09-21 | 2026-09-26 | 2026-09-28 | Y |  | chemo ePMA |  |  |  | Complex | Complex | 35 | 3
10 | LL-5917-169 |  | 2026-08-24 | 2026-09-24 | 2026-09-29 |  | N |  | inpatient ePMA |  |  |  | Simple | Simple |  | 2
11 | TANBRIM |  | 2026-08-29 | 2026-09-28 | 2026-10-02 |  | N |  | none |  |  |  | Moderate |  | 25 | 3
12 | STERSTER |  | 2026-09-02 | 2026-09-30 | 2026-10-05 |  | Y |  | chemo ePMA |  |  |  | Moderate | Moderate |  | 3
13 | AMX-7568-115 |  | 2026-09-08 | 2026-10-02 |  |  | N |  | chemo ePMA |  |  |  | Simple | Moderate |  | 2 | Awaiting pharmacy notification.
14 | NOVDAXU (XWX-3564) |  | 2026-09-13 | 2026-10-04 |  |  | Y |  | none |  |  |  | Moderate |  | 30 | 3
15 | PYRDROEL (HRX-1878) |  | 2026-09-18 | 2026-10-20 |  |  | N |  | chemo ePMA |  |  |  | Simple | Simple |  | 2 | Site selection expected next month.
16 | ORDRO | Completed | 2026-01-21 | 2026-02-20 | 2026-02-24 | 2026-03-02 | Y | 2026-06-17 | none |  |  | 2026-06-20 | Complex |  |  | 3
17 | GARTAN | Completed | 2026-03-12 | 2026-04-01 | 2026-04-06 | 2026-04-11 | N |  | chemo ePMA | 2026-04-26 | 2026-06-05 | 2026-06-10 | Moderate | Simple |  | 2
18 | VERQUI-01 | Completed | 2026-03-22 | 2026-04-21 | 2026-04-23 | 2026-05-01 | N |  | none |  |  | 2026-06-05 | Simple |  |  | 3
19 | SELMELT | Completed | 2026-04-11 | 2026-05-11 | 2026-05-15 | 2026-05-21 | Y | 2026-08-26 | chemo ePMA | 2026-06-05 | 2026-08-24 | 2026-08-29 | Complex | Complex |  | 3
20 | PEXMEL-02 | Completed | 2026-05-11 | 2026-06-10 | 2026-06-12 | 2026-06-20 | N |  | inpatient ePMA | 2026-07-05 | 2026-08-14 | 2026-08-19 | Moderate | Moderate |  | 2